## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: | Web Development
INTERN NAME: | Saniya Shaikh
DOCUMENT NAME: | TEST PLAN
CREATED ON: | 2026-01-31
Purpose of Document
A Test Plan is a detailed document that describes the test strategy, objectives, schedule, estimation, deliverables, and resources required to perform testing for a software product.
Test Plan helps us determine the effort needed to validate the quality of the application under test.
The test plan serves as a blueprint to conduct software testing activities as a defined process, which is minutely monitored and controlled by the test manager
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments are added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled

## TEST PLAN
TEST PLAN
PROJECT NAME | College Search Website
PROJECT ID | IAC-GPI-2026-WEB
INTERN NAME | Saniya Shaikh
PROJECT MANAGER | Harshada Topale
INTRODUCTION
(Brief introduction of the test strategies, process, workflow and methodologies used for the project)
The purpose of this Test Plan is to define the strategy, resources, and scope for verifying the College Search Website. This document ensures that the fuzzy search logic, database connectivity, and user interface meet the quality standards required for a centralized academic discovery platform.
SCOPE
In Scope
Functional testing of the PHP Search Engine and Fuzzy Logic accuracy. Validation of MySQL Database connectivity and data retrieval. UI/UX testing for responsiveness across mobile and desktop browsers. Security testing for SQL Injection prevention.
Out of Scope
User registration and student profile management (moved to future scope). Payment gateway integration for college application fees. Live API integration with external university servers.
QUALITY OBJECTIVE
(Mention the overall objective that you plan to achieve without your testing)
The primary objective is to ensure 100% of the core search functionalities pass without critical errors. Specifically, the system must handle typo-tolerant queries with a Levenshtein distance of 3 and maintain a search response time of under 2 seconds for a database of 10,000 records.
ROLES AND RESPONSIBILITIES
(Detail description of the Roles and responsibilities of different team members)
Role,Responsibility,Assigned To Test Lead / Intern,"Creating test cases, executing tests, and logging bugs in the Traceability Matrix.",Saniya Shaikh Project Mentor,"Reviewing test results, approving the Test Plan, and verifying critical bug fixes.",Vinith Christopher
TEST METHODOLOGY
OVERVIEW
A Waterfall-based testing approach will be used, where testing begins once the development of a specific module (like the database or search logic) is complete.
TEST LEVELS
Unit Testing: Testing individual PHP functions like db.php for connectivity. System Testing: Testing the end-to-end flow from search input to result card display. User Acceptance Testing (UAT): Verifying the portal meets the student discovery requirements
BUG TRIAGE
Bugs will be categorized as Critical (System crash/Security), High (Broken search), or Low (UI misalignment) and reviewed daily.
TEST COMPLETENESS
Testing is considered complete when all "Critical" and "High" priority bugs are closed and 100% of the test cases in the Traceability Matrix have been executed.
TEST DELIVERABLES
(Mention all the Test Artifacts that will be delivered during different phases of the testing lifecycle)
Test Plan Document (Current document). Traceability Matrix (Mapping requirements to test results). Final Bug Report (Summary of passed, failed, and skipped cases).
RESOURCE AND ENVIRONMENT NEEDS
TESTING TOOLS
XAMPP: For local Apache and MySQL server hosting. Chrome DevTools: For debugging CSS responsiveness and console errors. VS Code: For reviewing and fixing backend PHP logic.
TEST ENVIRONMENT
Hardware: Laptop with 8GB RAM, Windows 11 OS. Software: PHP 8.x, MySQL 8.0, and Google Chrome/Firefox browsers.
ADDITIONAL COMMENTS
The test environment will be refreshed before each major test cycle to ensure no "ghost data" affects the fuzzy search results.
TEST PLAN
ITEMS TO TEST | TEST DESCRIPTION | TEST START DATE | TEST END DATE | RESPONSIBLE PERSON | STATUS | COMMENTS
Local Server Setup | Verify that the Apache server and MySQL services are running correctly on XAMPP. | 2026-01-19 | 2026-01-19 | Saniya Shaikh | Passed | Environment configured for PHP 8.x.
SQL Schema Integrity | Check that all columns (Name, State, City, etc.) are correctly created with appropriate data types. | 2026-01-20 | 2026-01-20 | Saniya Shaikh | Passed | Primary keys and indexing verified.
Data Import Validation | Verify that the initial batch of 100 college records was imported without encoding issues. | 2026-01-21 | 2026-01-21 | Saniya Shaikh | Passed | Regional characters in institution names displayed correctly.
State/City Filters | . | 2026-01-25 | 2026-01-26 | Saniya Shaikh | Passed | AJAX-based city loading works without page refresh.
SQL Injection | Test inputs with special characters (' OR 1=1) to ensure database security. | 2026-01-27 | 2026-01-27 | Saniya Shaikh | Passed | Input sanitized via mysqli_real_escape_string.
UI Responsiveness | Check if college cards and navigation menus align correctly on mobile screens. | 2026-01-28 | 2026-01-28 | Saniya Shaikh | Passed | CSS Media Queries verified on Chrome mobile emulator.
Data Integrity | Verify that college contact links (email/phone) are correctly formatted. | 2026-01-29 | 2026-01-30 | Saniya Shaikh | Failed | Identified 5% of dead website links; added Google fallback.
Note on C17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To determine scope, you must – > Precise customer requirement > Project Budget > Product Specification > Skills & talent of your test team
Note on C24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The objective of the testing is finding as many software defects as possible; ensure that the software under test is bug free before release. To define the test objectives, you should do 2 following steps: > List all the software features (functionality, performance, GUI…) which may need to test. > Define the target or the goal of the test based on above features
Note on C40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: A Testing Type is a standard test procedure that gives an expected test outcome. all Testing Types are aimed at achieving one common goal “Early detection of all the defects before releasing the product to the customer. There are tons of Testing Types for testing software product. Your team cannot have enough efforts to handle all kind of testing. As Test Manager, you must set priority of the Testing Types > Which Testing Types should be focused for web application testing? > Which Testing Types should be ignored for saving cost? The commonly used testing types are: 1. Unit Testing 2. API Testing 3. Integration Testing 4. System Testing 5. Install/Uninstall Testing 6. Agile Testing You need to decide based on your project scope, time and cost the testing type(s) required for your project
Note on C48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Test Criteria is a standard or rule on which a test procedure or test judgment can be based. There’re 2 types of test criteria as following Suspension Criteria Specify the critical suspension criteria for a test. If the suspension criteria are met during testing, the active test cycle will be suspended until the criteria are resolved. Exit Criteria It specifies the criteria that denote a successful completion of a test phase. The exit criteria are the targeted results of the test and are necessary before proceeding to the next phase of development. Example: 95% of all critical test cases must pass.