## GPI - Project Charter
PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME | College Search Website
PROJECT SPONSOR | Tushar Topale
PROJECT MANAGER | Harshada Topale
EXPECTED START DATE | 16th December, 2025
EXPECTED COMPLETION DATE | 31st January, 2026
ESTIMATED COST | N.A.
GOALS, OBJECTIVES, DELIVERABLES
PROJECT OBJECTIVE (Objective of a project represents the output or what you want to accomplish by doing it.) | Develop a responsive web portal that allows students to discover educational institutions across India through verified data. It aims to simplify the search process using dynamic location filters for states and cities.
BUSINESS CASE (A business case provides justification for undertaking a project. It evaluates the benefit, cost and risk of alternative options and provides a rationale for the preferred solution. ) | This project reduces the time students spend navigating fragmented academic websites by providing a centralized, searchable database. It ensures higher accessibility to verified college information, improving the decision-making process for prospective applicants.
GOALS/METRICS (The project goal refers to achieving a desired outcome (performance goal) at a specific end date (time goal) employing a specific amount of resources (resource goal).) | Successfully implement a two-tier filtering system and a functional fuzzy search bar with a result load time of under two seconds. The portal must achieve 100% responsiveness on mobile devices and cross-browser compatibility.
EXPECTED DELIVERABLES (Describe the quantifiable goods or services that must be provided upon the completion of a project.) | A fully functional web application containing PHP source code and a customized CSS stylesheet. Additional deliverables include the MySQL database schema for college records and comprehensive technical documentation.
PROJECT SCOPE AND SCHEDULE
WITHIN SCOPE (This is functions and information which should be taken into account(estimated) in the development at the first stage. Or the stage for the development perios.) | Development of the frontend interface using HTML5 and CSS3 Grid, along with backend PHP logic for search and location filtering. Integration of fuzzy matching algorithms and a secure MySQL database connection are also included.
OUTSIDE OF SCOPE (This is functions which are planned to be done, but they are not reqired on the first stages.) | This project excludes user authentication systems, student login profiles, and online application submission portals. Advanced features such as real-time chat support or integrated payment gateways are not part of this development stage.
PROJECT RESOURCES AND COSTS
PROJECT TEAM (Mention the number of resources, who will be working on the project.) | A core team consisting of one Full-stack Developer for PHP/SQL logic and one UI/UX Designer for responsive CSS layouts. Both resources will collaborate on data integration and final system testing throughout the project lifecycle.
SUPPORT RESOURCES (Mention all the other resources that will be needed for the completion of the project.) | Necessary resources include a local development environment (XAMPP/WAMP), a code editor like VS Code, and access to a reliable MySQL database. Ongoing support will require a web hosting platform and domain for live deployment.
COST ALLOCATION (Mention the cost of all the resources on an hourly/monthly/yearly basis. This will help to stick on to the project budget.) | Costs are primarily allocated to development hours for backend programming and frontend styling. Secondary allocations include potential expenses for web hosting services and domain registration for the portal’s production environment.
PROJECT STAKEHOLDERS AND CUSTOMERS
PROCESS OWNER (Mention the Project Owner) | The Lead Developer serves as the process owner, overseeing the entire software development lifecycle from database design to UI deployment. They are responsible for maintaining coding standards and ensuring project milestones are met.
KEY STAKEHOLDERS (Mention all the stake holders involved in the project.) | Key stakeholders include educational consultants, college administrators, and the project development team. These groups provide the necessary academic data and technical expertise to build and maintain the platform.
END CUSTOMER (Mention the client name.) | The primary end customers are prospective students and parents seeking a streamlined way to find colleges in India. Educational institutions looking for a platform to showcase their verified data also serve as secondary customers.
PROJECT RISKS, CONSTRAINTS, ASSUMPTIONS
RISKS (Risk is any unexpected event that can affect your project — for better or for worse. Risk can affect anything: people, processes, technology, and resources.) | Potential risks include data inconsistencies within the college database and vulnerabilities to SQL injection if inputs are not properly sanitized. Additionally, unexpected changes in browser rendering could impact the responsive grid layout.
ASSUMPTIONS (An assumption is any project factor that is considered to be true, real, or certain without empirical proof or demonstration.) | It is assumed that the provided database of college information is accurate and that the end-users have basic internet connectivity. We also assume the local server environment remains stable during the entire testing phase.
CONSTRAINTS (Project constraints are anything that restricts or dictates the actions of the project team.) | The project is restricted to a local server environment (XAMPP) and a fixed development timeline. Actions are dictated by the available college dataset and the requirement to maintain high performance without external API dependencies.
MILESTONES
MILESTONE 1- Requirement Gathering ("Mention Completion Date in MM-DD-YYYY format. Requirement gathering is marked as complete after submission of SRS document") | Complete by 27-12-2026. This phase concludes once the functional requirements for search filters and database fields are documented and approved.
MILESTONE 2 - Planning ("Mention Completion Date in MM-DD-YYYY format. Planning phase is considered after a duly completed Work Breakdown Structure (WBS), Project Schedule and RAID logs") | Complete by 05-01-2026. This milestone is achieved after defining the file structure, database schema, and establishing the project schedule and risk logs.
MILESTONE 3 - Design ("Mention Completion Date in MM-DD-YYYY format. Design stage is considered complete after submission of Design Specifications and Wireframe files") | Complete by 15-01-2026. This stage is finished following the completion of the UI wireframes, CSS style guides, and responsive layout mockups for the portal.
MILESTONE 4 - Development ("Mention Completion Date in MM-DD-YYYY format. Development stage is considered complete after submission of Design Specifications and Wireframe files") | Complete by 22-01-2026. Development is marked complete after the PHP logic, SQL queries, and frontend integration are fully coded and functional.
MILESTONE 5 - Testing ("Mention Completion Date in MM-DD-YYYY format. Testing stage is considered complete after submission of Test Reports") | Complete by 26-01-2026. This phase is considered final after conducting cross-browser testing, mobile responsiveness checks, and verifying search accuracy.
MILESTONE 6 - Deployment ("Mention Completion Date in MM-DD-YYYY format. Deployment stage is considered complete after sybmitting the ") | Complete by 28-01-2026. The deployment stage is finished after successfully hosting the portal on the local server and submitting the final documentation.
MILESTONE 7 - Closure ("Mention Completion Date in MM-DD-YYYY format. Project closure is considered complete after handover of leasson learnt log, project report and installation guide") | Complete by 31-01-2026. This final milestone is achieved after the official handover of the project report, installation guide, and the lesson learnt log to the stakeholders.