## RAID LOG
| RAID Log | Should you face any difficulty in completing the RAID Log, please refer to 'Project Planning' Workshop, https://script.google.com/macros/s/AKfycbz1vCRZzDZf9SkwX8gv1DzKe59fupHWWehSUu0jeTsiZZxn3YdNVAD1sHDLDUanbJ5O/exec | [8 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 8 | 1 | 1 | 0 | 1 | 1 | Instruction to use the RAID log template: • All fields must be duly filled • The descriptions for what to be filled in each of the fields are provided in the template. • Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes. • Understand what risks, assumptions, issues, and dependencies are from the description provided in the methodology document • Select the category of RAID from the dropdown menu provided in the “RAID category” field in the template. • Provide a valid description of the RAID category that you have selected in the “description” field provided. • Describe the impact the RAID category you have selected will have on the project in the “impact field”. • Describe how the impact of the selected RAID category can be reduced on the project in the “mitigation field” in the template. • Mention the responsible person for working on the selected RAID category in the “owner” field in the template. • Select the priority with which the selected RAID category needs to be mitigated. The following levels of priority are given in the drop-down menu. Select; o Negligible: if the RAID category is not going to make an impact on the project o Low: if the raid category is going to make very small impacts on the project o Moderate: if the RAID category is going to make a few impacts which can affect the project adversely. o High: if the RAID category is going to make major impacts on the project adversely. o Critical: if the raid category is going to affect the project at any stage. • Provide risk priority number based on the priority selected for the RAID category selected. • Select the status of the RAID category selected. Two options are provided in the drop-down menu. Select; o Open: if the responsible person is still working on the RAID category selected. o Closed: if the responsible person has worked on the RAID category and is solved.
| Project title: | College Search Website |  | Project Id: | IP -7152 | Project Manager: | Harshada Topale |  |  | Assumption | 3 | 0 | 0 | 3 | 0 | 0
[10 empty] | Issue | 4 | 0 | 1 | 0 | 0 | 0
| DOCUMENT VERSION: | Final |  | Last Updated date: | 2026-01-30 | Project Team Lead: | Vinith Christopher |  |  | Dependency | 5 | 0 | 4 | 1 | 0 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 20 |  |  |  |  | 13
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Risk | Manual Data Entry Errors: Typing mistakes in college emails or phone numbers during bulk entry. | Prospective students cannot contact institutions. | Perform weekly data audits and use SQL DISTINCT queries to find duplicates. | Saniya Shaikh | High | 48(8*6) | Open | Risk
2 | Risk | SQL Injection: Lack of input sanitization in the search bar. | Unauthorized database access or data deletion. | Use mysqli_real_escape_string for all PHP search queries. | Saniya Shaikh | Critical | 81(9*9) | Closed | Assumption
3 | Assumption | Data Availability: Assuming all colleges have publically listed contact info. | Difficulty in populating the database for specific remote states. | Use Google Search fallback links if official websites are unavailable. | Saniya Shaikh | Moderate | N/A | Open | Issue
4 | Issue | Filter Misalignment: Dependent "City" dropdown not appearing after "State" selection in certain browsers. | Users cannot narrow down search results effectively. | Debugged JS/PHP logic to ensure the form submits on onchange event. | Saniya Shaikh | High | N/A | Closed | Dependency
5 | Dependency | XAMPP Environment: The project development depends on a local Apache/MySQL server setup. | Development stops if the local server crashes or has port conflicts. | Maintain a backup of the SQL export file (.sql) and configuration settings. | Saniya Shaikh | Moderate | N/A | Open
6 | Risk | UI Responsiveness: Search bar and college cards breaking on small mobile screens. | Poor user experience for mobile visitors (majority of traffic). | Implement CSS Media Queries and use Flexbox/Grid for the results layout. | Saniya Shaikh | High | 56(8*7) | Closed | Open
7 | Assumption | Hosting Compatibility: Assuming the selected hosting platform supports the specific PHP version used in development. | Check hosting server specifications (PHP 8.x) before the final deployment phase. | Check hosting server specifications (PHP 8.x) before the final deployment phase. | Saniya Shaikh | Moderate | N/A | Open | Closed
8 | Dependency | Project Documentation Guidelines: Completion of the final report depends on receiving the 'List of Deliverables' from the Live Project workflow. | Delay in final submission despite the code being ready. | Regularly monitor the Cloud Counselage portal for updated instruction sheets and templates. | Saniya Shaikh | High | N/A | Open
9 | Issue | Manual Entry Fatigue: The massive volume of manual data entry (200-500 colleges per state) is leading to increased typographical errors. | Lowered data quality and inaccurate contact details for students. | Created an Excel-based validation sheet to scrub data before importing it into MySQL. | Saniya Shaikh | High | N/A | Open | Critical
10 | Risk | Browser Cache Conflicts: Users might see outdated college data or broken CSS due to aggressive browser caching. | Inconsistent UI presentation across different user devices. | Use versioning for the style.css file link (e.g., style.css?v=1.1) to force cache refresh. | Saniya Shaikh | Low | 24(4*6) | Open | High
11 | Risk | Session Timeout during Data Entry: PHPMyAdmin or the local server session timing out while manually entering large batches of data. | Potential loss of unsaved progress and repetitive work. | Increase the session.gc_maxlifetime in php.ini and save progress after every 10 records. | Saniya Shaikh | Moderate | 35(5*7) | Closed | Moderate
12 | Dependency | Database Server Uptime: Project relies on the local MySQL server remaining active and uncorrupted. | Inability to test or demonstrate the college search functionality. | Keep a daily .sql export backup of the college_portal database. | Saniya Shaikh | High | N/A | Open | Low
13 | Assumption | Browser Compatibility: Assuming the JavaScript onchange event for city filters works across all modern browsers. | The dynamic filtering feature might fail for users on older browser versions. | Use standard Vanilla JS and test on Chrome, Firefox, and Edge. | Saniya Shaikh | Moderate | N/A | Open | Negligible
14 | Issue | Slow Query Performance: Search becomes sluggish as the college count exceeds 1,500 entries. | Poor UI responsiveness and high user drop-off rate. | Added SQL Indexes to the name, city, and state columns for faster retrieval. | Saniya Shaikh | High | N/A | Closed
15 | Dependency | Final Approval & Feedback: The project cannot be marked as "Complete" without a formal review by the mentor. | Delay in internship certification and final grade assignment. | Submit regular updates during weekly meetings to ensure the project aligns with requirements.Harshada | Harshada Topale | High | N/A | Open
16 | Dependency | Receipt of "List of Deliverables" from portal. | Cannot finalize project documentation. | Regularly check the Cloud Counselage portal for updates. | Harshada Topale | High | N/A | Open
17 | Issue | API Documentation Gap: Incomplete instructions regarding the integration of external college listing APIs. | Difficulty in automating data retrieval, leading to forced manual entry. | Requested clarification through the project manager for the "List of Deliverables". | Vinith Christopher | High | N/A | Closed
18 | Risk | Server-Side Security Breach: Potential vulnerability in the hosting provider's shared server environment. | Compromise of all hosted college data and intern database access. | Choose a hosting platform with SSL support and regular server-side patching. | Hosting Provider / IT Admin | Critical | 70(10*7) | Open
19 | Risk | Footer Social Icon Alignment: Minor CSS misalignment of social media icons in the footer on ultra-wide monitors. | Negligible effect on site functionality or core user search experience. | Use a standard CSS Flexbox container with justify-content: center to ensure centering across all resolutions. | Saniya Shaikh | Negligible | 4(2*2) | Open
20 | Risk | Non-standard Font Rendering: Occasional fallback to system fonts if the "Inter" Google Font fails to load due to slow CDN. | Small impact on visual branding; the site remains fully readable and functional. | Defined high-quality system font fallbacks (sans-serif) in style.css to maintain a professional look. | Saniya Shaikh | Low | 12(4*3) | Closed
21
22
23
24