## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: | Web Development
INTERN NAME: | Saniya Shaikh
PROJECT NAME: | College Search Website
DOCUMENT NAME: | Lessons Learnt Log
CREATED ON: | 2026-01-29
Purpose of Document
Lessons Learned Logs are used to capture and share knowledge about what has worked well and what could have been done differently during the planning, management and delivery of an improvement project.
They help others learn from the project team's experience. Lesson Learned Logs: Help support a learning culture.
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments may be added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled
5. The descriptions for what to be filled in each of the fields are provided in the template.
6. Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes.

## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | College Search Website |  |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT ID | IP -7152
PROJECT MANAGER | Saniya Shaikh
PROJECT SPONSOR | Cloud Counselage
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
| MENTION THE DATE ON WHICH THE MATTER WAS RAISED | DESCRIBE THE EVENT THAT WAS RAISED | MENTION WHICH CATEGORY THE EVENT WAS RELATED TO | MENTION YES OR NO | MENTION THE RECOMMENDATIONS THAT WAS SUGGESTED FOR SOLVING THE EVENT IF ANY | MENTION THE ACTION SELECTED FOR SOLVING THE VENT | MENTION THE RESPONSIBLE PERSON FOR SOLVING THE EVENT | SOLVED/ PENDING | MENTION IF ANYTHING ELSE OCCURRED DURING THE TIME OF THE MENTIONED EVENT
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
1 | 2026-01-04 | Database schema required multiple revisions after initial planning. | Planning | Yes | Define all required data fields (email, contact, courses) before coding. | Finalized SQL schema in the planning phase to avoid mid-code changes. | Lead Developer | Solved | Improved code efficiency.
2 | 2026-01-12 | CSS Grid layout was breaking on older mobile browsers. | Design | Yes | Use standard Flexbox/Grid properties with browser prefixes. | Implemented responsive media queries and tested on multiple devices. | UI Designer | Solved | Achieved 100% mobile responsiveness.
3 | 2026-01-22 | Metaphone search results were too broad for very short queries. | Development | No | Adjust Levenshtein distance threshold for specific keyword lengths. | Tuned the fuzzy search algorithm logic to balance accuracy and speed. | Lead Developer | Solved | Search accuracy improved by 20%.
4 | 2026-01-28 | Missing sample data for certain Indian states during testing. | Execution | Yes | Source a comprehensive, verified dataset early in the project. | Manually verified and added test records for all 28 Indian states. | Data Analyst | Solved | Database now has full regional coverage.